## SMH
Job# | Loc. | Tasks | Bal Date | Com Date | Install | Tech | Design | Lead | Last Modified
ABAM2 | RMC | MRG EP Demo | [6 empty] | Issac Magallanes
4-0362 | Mb04 CV 15/16 | Demo Phase Roush-in 8/23 ¦ Setra Low Tap (Temp'd for now) ¦ Adair Install
3-0385 | Mb03 CV-ICU | Verify, Nurse Call: CX 8/20-8/24
4-319 | Sec. Staff Space | Generose - Graphic, Controller Naming ¦ Tom / Adair
3-0362 | Laundry Bld | RR demo - check back 8/22 ¦ FCU Steam Vlv at office
4-0138 | Dom-Mom Magneto | VAV/FCU ready for Point checkout, 9 VAV, 1 FCU, 8 F/s, 2 Hx, 1 O2 Seas, 1 Duct Sens
4-0275 | MB00M | MR-34
4-0363 | MB CLG CAP UPGRADE | Chiller 1.2_FEC-006 Head-End Clean-up
4-0426 | Mb02 | Locker Rooms
4-0254 | Fr07 AFMS | FS-8 AFMS Install
4-0385 | Brach03 | 11 Vlvs + 6 T-Stats Demo
4-0073 | Al03 | Keeping Open
Test | Building | General Notes 2 | 9/30 | 10/2 | Pipe and Install panel | VAV Checkout | Finish Redlines | Submit RFI
Test | Building | General Notes 2 |  | 10/2 |  | VAV Checkout |  | Submit RFI

## RMH
Job# | Loc. | Tasks | Bal Date | Com Date | Install | Tech | Design | Lead | Last Modified
4-0356 | Ei00L Cafeteria | FC Bus Download/Vout
3-0195 | EI005 | Condensate pump replacement
3-0216 | Ei07-3
4-0532 | Ei005 MR6 | Replace Steam Coil
5-0534 | Ch04 | Replace Iso Dmp; some night after 10 pm
3-0423 | Ei005-MR1 | Wet Filter DP's!
4-0114 | EiPH | EFI Iso Dampers
4-0201 | Ch01 | Pipe/Device VAVs
4-0271 | JB - Labor | Fix piping for North side F/S Dampers, Rough-In, Stat relocates
4-0272 | JB - Material | Material Only
3-0435 | PTI Vibration | JB S-105A, JB S-105B, Ei58, EiR8
4-0277 | Ch005 | FC + N2 Clean-up, wire valves, upgrade between VAV
4-0322 | Ch01 | Cx 9/26
4-0485 | Ei005-67 | Facilities Shot ¦ Panel: Relocate/Writing
4-0499 | Ei01-106A | Cx