## SMH
Job# | Loc. | Tasks | Bal Date | Com Date | Install | Tech | Design | Lead | Last Modified
ABAM | RMC | MRG EP Demo | [6 empty] | Issac Magallanes
4-0362 | Mb04 CV 15/16 | Demo Phase Roush-in 8/23 ¦ Setra Low Tap (Temp'd for now) ¦ Adair Install
3-0385 | Mb03 CV-ICU | Verify, Nurse Call: CX 8/20-8/24
4-0319 | Sec. Staff Space | Generose - Graphic, Controller Naming ¦ Tom / Adair
3-0362 | Laundry Bld | RR demo - check back 8/22 ¦ FCU Steam Vlv at office
4-0138 | Dom-Mom Magneto | VAV/FCU ready for Point checkout, 9 VAV, 1 FCU, 8 F/s, 2 Hx, 1 O2 Sens, 1 Duct Sens | [6 empty] | Issac Magallanes
4-0275 | MB00M | MR-34
4-0363 | MB CLG CAP UPGRADE | Chiller 1.2_FEC-006 Head-End Clean-up
4-0426 | Mb02 | Locker Rooms
4-0254 | Fr07 AFMS | FS-8 AFMS Install
4-0073 | Al03 | Keeping Open
4-0520 | Mb05 East Tower | Mb05 East Fit Up. Rough-In starts 10/14. | Jul 2025 | Aug 2025 | Adair-Walk Through 6 F/S Damper. 16 Pt Rm VAV's, 14 normal VAV's, 24 RadVlvs. Rough-in starts 10/14 | Checkout-Months. Initial Walk-through, site investigation | Order Material, submittal: HUM VLV | Walk Through | Issac Magallanes
4-0490 | Mh4-5-7 | Cons of MH: Pneumatic Demo on Marion 4-5-7. Bakken Project |  |  | Demo |  |  |  | Tony Nigon
4-0522 | Mh3-4 | MH 3-4th Fl Remodel Rasmussen Job |  |  | Pnuematic Demo |  |  |  | Tony Nigon

## RMH
Job# | Loc. | Tasks | Bal Date | Com Date | Install | Tech | Design | Lead | Last Modified
3-0216 | Ei07 | [7 empty] | Colton
3-0423 | PTI Vibration | JBS-105A, JBS-105B, EIS-8, EIR-8 | [6 empty] | Colton
3-0435 | Ei00S-MR1 | Wet Filter DP's | [6 empty] | Colton
4-0114 | EiPH | EF-1 Iso Dampers | [6 empty] | Colton
4-0201 | Ch01 | Download/checkout | [6 empty] | Colton
4-0271 | JB - Labor | Fix piping for North side F/S Dampers, Stat Relocates, Pipe/Device VAVs | [6 empty] | Colton
4-0272 | JB - Material | Material Only
4-0277 | Ch00S | Humidifier Install, F/S Dmp in Breakroom | [6 empty] | Colton
4-0322 | Ch01 | Pipe/Device VAV | [6 empty] | Colton
4-0350 | Jb01 | Leak Detection | [6 empty] | Colton
4-0356 | Ei00L Cafeteria | Download/checkout | [6 empty] | Colton
4-0391 | Ei01-360 | Install of new VAV - Adair | [6 empty] | Colton
2-0120 (temp) | Gu19, Gu20, Al09 | Demo phase 1 on Gu19 until 10/24. NO JOB NUMBER YET. Status of Gug19? |  |  | Pneumatic Demo on Gug19 til 10/24. Phase 2 Alfred starts in Feb 2025 |  |  | Dominate | Tony Nigon
4-0435 | Si11 | Project 4. Phase 2 starts 3/17/25 |  |  | 3/17/25 Phase 2 |  |  |  | Tony Nigon
4-0440 | Albert Lea ED | Pneumatic Demo, work starts in December (?) |  |  | Pneumatic demo |  |  |  | Tony Nigon
5-0473 | Go15 | New Procedure Room, pneumatic demo |  |  | demo |  |  |  | Tony Nigon
5-0478 | Mayo 20/21 | Demo of 1 AHU on each floor-Done? |  |  | Demo |  |  |  | Tony Nigon
4-0485 | Ei00S-67 Facilities Shop | Cx | [6 empty] | Colton
4-0526 | Ch00S | MR-56 Starts 11/4 | [6 empty] | Colton
4-0436 | Ei00L | Relaxation Room - on hold | [6 empty] | Colton
4-0532 | Ei00S-MR6 | Replace Steam Coil / Low Limits | [6 empty] | Colton
5-XXXX | Ch00S-227 | Vault G - 3 Cooling only VAVs |  |  |  |  | Submittal |  | Colton
3n53-0338 | Ei00L | Data Center and Dock Cutovers |  |  |  | Data center and Dock Cutovers |  |  | Sagan
3n53-0335 | Ei00S | Final Closeout |  |  |  | As Builts in panels, Green Labels |  |  | Sagan
3n53-0339 | Cn02P | S-65 and 66 Cutovers |  |  |  | Final Closeout |  |  | Sagan
3n53-0344 | Ch00S | Domestic Hot Water Pumps |  |  |  | Verify Final Closeout |  |  | Sagan